## Phase I
Work Order Id | Task Description | Task Type | Comments | Status
1 | Make CSS changes to question to make comments look smaller | Enhancement |  | Done
2 | Show user details for the comments entered | Enhancement |  | Done
3 | Make user profile setting page more presentable and working | Enhancement |  | Done
4 | Change question page to make it work on bootstrap tags instead of table tags | Enhancement |  | Done
5 | the controls are not looking nice one other screens after changing controls on question screen | Enhancement |  | Done
6 | Show user name and other details in the header once user logs in | Enhancement |  | Done
7 | Show validation summary on all the pages | Enhancement |  | Done
8 | Make enter show in the Question answer and question | Enhancement |  | Done
9 | Add paginations on home page for questions | Enhancement |  | Done
10 | Read region from Web config and not from busconstant | Issue |  | Done
11 | Buissness rules on question and request category page | Issue |  | Done
12 | Google, facebook and twitter login feature using MVC | Enhancement |  | Done
13 | Logoff does not work properly in production | Issue |  | Done
14 | Redirect users to login pages when needed, also carry the data which was supposed to be posted | Issue |  | Done
15 | Work on profile page to make it look better on mobile devices | Issue |  | Done
16 | Multi select categories | Enhancement |  | Done
17 | Redirect http calls to https | Enhancement |  | Done
18 | Add default site logo on website header | Enhancement |  | Done
19 | Add tinyMCE rich HTML texteditor | Enhancement |  | Done
20 | Make partial views for question page | Enhancement | MVC has some issues dealing with it | Pending
21 | Upvote and downvote links are not working | Issue |  | Done
22 | Share Question on social networks buttons feature | Enhancement |  | Done
23 | Download qaulity google and facebook profile pictures in server folders | Enhancement |  | Done
24 | Meta tag description is not raw html | Issue |  | Done
25 | Show profile picture on question page for users | Enhancement |  | Done
26 | Keep question title in the link on post back at quesiton page | Issue |  | Done
27 | Separate controller functions | Enhancement |  | Done
28 | Make cards | Enhancement |  | Done
29 | Make Validation summary like bootstrap | Enhancement |  | Done
30 | tinyURL for sharing question | Enhancement |  | Done
31 | SSL certificate expiration | Issue |  | Done
32 | Add admin to nav bar and remove for regular users | Enhancement |  | Done
34 | Design and develop feedback screen | Enhancement |  | Done
35 | Add help texts | Enhancement |  | Done
36 | Work on points system | Enhancement |  | Done
37 | Does not fit right on mobile devices | Issue |  | Done
38 | Delete question views when question is deleted | Issue |  | Done
39 | Create social network accounts for sharing |  |  | Done
40 | Make font size across the site better | Issue |  | Done
41 | Request tags page is not working | Issue |  | Done

## Phase II
Work Order Id | Task Description | Task Type | Comments | Status
1 | Redesign views like google analytics and find place on question page to show views | Enhancement
2 | Edit question should go on the other page | Enhancement |  | Done
3 | Make SEO related changes | Enhancement
4 | Work on deployment process | Enhancement
5 | Add settings to the cards | Enhancement
6 | Make different branches for different environment | Enhancement
7 | Add source column to question view to see from where users are viewing the page | Enhancement
8 | TF-IDF Implementation | Enhancement
9 | Add points progress bar | Enhancement
10 | Design leaderboard | Enhancement
11 | Make datasetrows convertible to business objects | Enhancement
12 | Fix the error on 1st time load of question page | Issue
13 | Tag User | Enhancement
14 | Cancel button on answer comment edit | Issue
15 | Upvote and downvote links for question comments and question answer comments | Enhancement
16 | Email confirmation feature | Enhancement
17 | Forgot password functionality | Enhancement
18 | Welcome email after registration | Enhancement
19 | Design user roles | Enhancement
20 | Create a template page to have consistancy all over the site | Enhancement
21 | Show more comments link | Enhancement
22 | Add footer | Enhancement
23 | Design profile links on header better | Enhancement |  | Done
24 | upgrade tools | Enhancement
25 | show the time when post was created | Enhancement |  | Done
26 | Exception on saving account settings page | Issue |  | Done
27 | Description on request page should be longer or bigger/ Increase column size too | Enhancement |  | Done
28 | Make better login and register pages | Enhancement |  | Done
29 | Store user credentials in cookies obviously encrypted | Enhancement
30 | Paging at the bottom of the page | Enhancement |  | Done
31 | Fix login click for mobile users | Issue
32 | Add Google Adsense | Enhancement |  | Done
33 | Create fake user accounts | Enhancement |  | Done
34 | Remove tags from ask question page | Enhancement |  | Done
35 | Make tinyMCE only what is needed for | Enhancement |  | Done
34 | upload profile picture | Enhancement |  | Done

## Demo Steps
Step Id | Task | Status
1 | Delete question and answers with post votes and notifications